## Software Project Scope
PROJECT SCOPE DOCUMENT
ORGANIZATION | VITAP
PROJECT NAME | Credit Card Fraud Detection project
PROJECT LEAD CONTACT INFO
NAME | Valiveti Manikanta Bhuvanesh
PHONE | 9014914993
Reg No | 19BCD7088
EMAIL | manikanta.19BCD7088@vitap.ac.in
DATE PREPARED | 11th December 2021
BEGIN DATE | END DATE | PROJECT DURATION
6th December 2021 | 11th December 2021 | 5 Days
PROJECT TEAM
NAME | Reg No | ROLES
TARINI GUTTULA | 19BCE7758 | Documentation
POPURI HARSHA VARDHAN | 19BCI7039 | Data Scientist
GANGARAPU BALASUBRAMANYAM | 19BCE7681 | Data Analyst
ROKKAM ANIRUDH | 19BCD7081 | Data Analyst
PROJECT
INTRODUCTION
Credit card fraud has increased dramatically in recent months. The objective of this R project is to create a classifier capable of accurately detecting credit card fraud. a fraudulent and non-fraudulent call by applying these ML algorithms.This project will show you how to classify data using machine learning techniques in a real context.
BACKGROUND
These days, Using technologies such as the phishing method to commit online banking fraud entails transmitting and withdrawing funds from a banker's account without the banker's authorization. Using machine learning methods and neural networks, this study aims to create a model that can accurately identify fraud and nonfraud transactions.
RESOURCE REQUIREMENTS
Credit card dataset and Rstudio
PROJECT SUMMARY
PHASE ONE | HOURS
Prepare Dataset | 1 hour
Data pre-processing,Data cleaning | 8 hours
MoM(2), | 2 hours
PHASE TWO | HOURS
Data Modeling,Prediction | 7 hours
Final report | 48 hours
Final PPT | 36 hours
MOM(1) | 2 hours
MILESTONES
EST DELIVERY DATE | PROJECT MILESTONE TITLE
12th december | Credit Card Fraud Detection
TIMELINE
6th december - 12th december (6 days)